## Project Planner
Project eTicketing Timeline
[5 empty] | Vendor | [5 empty] | Intikom | [6 empty] | Intikom & Vendor | [7 empty] | Go live
Task Desc | Note | PERCENT COMPLETE | 2023-03-01 | [25 empty] | 2023-04-01
|  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
- Login LDAP - Session as user from LDAP - Session as supervisor from LDAP - Dasboard user - Dasboard supervisor - New Ticker - Summary Ticket - Email notificarion from user request - Rating submit - Complain submit - Meeting and testing task 1 | Task 1 is considered complete and running well on the Intikom server | 25% | bar: 2023-03-01 6 to 2023-03-01 16
- Assign ticket to agent - Create ticket for agent - Agent request - create ticket for agent - Summary Ticker - Data Agent - Data Category - Email notification form supervisor module - Meeting and testing task 2 | Task 2 is considered complete and running well on the Intikom server | 50% | bar: 2023-03-01 13 to 2023-03-01 17
-Agent dasboard - Summary ticket - Request extend SLA - Email notification form agent module - Testing apps by Intikom teams - Meeting and testing task 3 | Task 3 is considered complete and running well on the Intikom server | 75% | bar: 2023-03-01 20 to 2023-03-01 21; 2023-03-01 23 to 2023-03-01 24; 2023-03-01 27
- Manajer dasboard - Data supervisor - Data Agent - Data Category - Data SLA - Report Ticket - Testing apps by Intikom teams - Meeting and testing task 4 - Go live | The BAST project will be signed by the Intikom if the apps are considered running functionally and no bugs | 100% | bar: 2023-03-01 28 to 2023-03-01 31; 2023-04-01 3 to 2023-04-01 6

## Calulation
SLA Response
ex | ditugaskan * | sla respon minute* | sla respon* | response | today | hasil | hasil rumus | send
rumus |  |  | = ditugaskan + sla repon minute | > ditugaskan | > response
1 | 2023-03-15 | 30 | 2023-03-15 00:30 |  | 2023-03-15 00:20 | 1 | sla respoon < today
2 | 2023-03-15 | 30 | 2023-03-15 00:30 |  | 2023-03-15 00:40 | 0 |  | email
3 | 2023-03-15 | 30 | 2023-03-15 00:30 | 2023-03-15 00:20 | 2023-03-15 00:40 | 1
4 | 2023-03-15 | 30 | 2023-03-15 00:30 | 2023-03-15 00:40 | 2023-03-15 00:50 | 0
SLA Ticket
ex | response* | sla ticket minute* | sla ticket* | resolved | close | today | Hasil | hasil rumus | send
rumus |  |  | = response + sla ticket | > response | > = resolved | > sla ticket
1 | 2023-03-15 | 60 | 2023-03-15 01:00 |  |  | 2023-03-15 00:20 | 1
2 | 2023-03-15 | 60 | 2023-03-15 01:00 |  |  | 2023-03-15 01:20 | 0
3 | 2023-03-15 | 60 | 2023-03-15 01:00 |  | 2023-03-15 00:20 | 2023-03-15 02:40 | 1
4 | 2023-03-15 | 60 | 2023-03-15 01:00 |  | 2023-03-15 01:20 | 2023-03-15 02:40 | 0
5 | 2023-03-15 | 60 | 2023-03-15 01:00 | 2023-03-15 01:40 | 2023-03-15 01:50 | 2023-03-15 02:50 | 0
6 | 2023-03-15 | 60 | 2023-03-15 01:00 | 2023-03-15 01:40 |  | 2023-03-15 02:20 | 0
7 | 2023-03-15 | 60 | 2023-03-15 01:00 | 2023-03-15 00:40 |  | 2023-03-15 02:20 | 1